UNIT 2 MINI PROJECT

AGILE PROJECT PLANNING

Enterprise Student Record and Academic Management Platform

Prepared as an Agile Mini Project

Student Name: Shrawani Dipak Toge

PRN No:2125UDSF1082
Department: Artificial Intelligence and Data Science
Academic Year: 2026–27

# 1. INTRODUCTION

## 1.1 Project Overview

The Enterprise Student Record and Academic Management Platform is a proposed software product for managing student and academic information in a higher-education institution. The Unit 1 project established the business problem, users, requirements, product vision, MVP and roadmap. This Unit 2 mini project converts that product discovery work into an Agile development plan.

The Agile approach divides the product into manageable features and delivers them incrementally through short development Sprints. The project uses Scrum concepts such as Product Owner, Scrum Master, Development Team, Product Backlog, User Stories, Acceptance Criteria, Story Points, Sprint Planning, Scrum Board, Sprint Review and Sprint Retrospective.

## 1.2 Purpose of Unit 2

Translate the Unit 1 product vision into Agile deliverables.

Break the product into Epics and User Stories.

Define measurable Acceptance Criteria.

Prepare and prioritize the Product Backlog.

Estimate effort using Story Points.

Plan development Sprints and Sprint Backlogs.

Define a Scrum Board and Scrum ceremonies.

Compare Agile frameworks and recommend a suitable approach.

## 1.3 Product Scope

User authentication and role-based access.

Student registration and profile management.

Course and subject registration.

Attendance management.

Examination and result management.

Academic reports and dashboards.

Notifications for important academic information.

# 2. STUDY OF BUSINESS PROBLEM AND PRODUCT VISION

## 2.1 Business Problem

Academic information is often maintained through multiple records, spreadsheets or disconnected systems. This can make it difficult for students, faculty and administrators to quickly access accurate information. Attendance, courses, examinations, results and reports may require repeated manual work. The proposed platform addresses this problem through a centralized digital system.

## 2.2 Product Vision

“Develop a secure and user-friendly Student Record and Academic Management Platform that enables educational institutions to efficiently manage student records, attendance, academic performance, course registration and reporting through a scalable web-based application.”

## 2.3 Mission

The mission is to transform manual or disconnected academic record management into an organized, accessible and secure digital system that helps each user complete academic tasks efficiently.

## 2.4 Primary Users

| User | Main Needs |
| --- | --- |
| Students | View profile, courses, attendance, examinations, results and reports. |
| Faculty Members | Manage courses, student information and attendance. |
| Academic Administrators | Manage records, users, courses and reports. |
| Examination Cell Staff | Manage examinations, marks and results. |
| IT Support Personnel | Maintain availability, security and technical operation. |

## 2.5 Business Benefits

Centralized academic information.

Reduced manual effort and duplicate data entry.

Faster access to student and academic records.

More efficient attendance and result management.

Improved reporting.

Better security through role-based access.

Incremental delivery and continuous improvement.

## 2.6 Success Criteria

Users can log in according to their assigned roles.

Students can access relevant academic information from one dashboard.

Faculty can record attendance efficiently.

Authorized staff can manage examinations and results.

Administrators can generate standard reports.

Restricted information is not accessible to unauthorized users.

The system remains understandable, reliable and maintainable.

# 3. AGILE PRODUCT VISION AND EXPECTED OUTCOMES

## 3.1 Overall Product Objective

The objective is to build the most important academic management capabilities first and deliver them in small, testable increments. Each Sprint should produce a usable improvement to the product.

## 3.2 Expected Software Capabilities

Secure user login and role-based access.

Student registration and profile management.

Course management and course registration.

Attendance recording and viewing.

Examination and result management.

Academic reporting.

Notifications and role-specific dashboards.

## 3.3 Project Constraints

Limited student development time.

Limited development resources.

Need for accurate academic data.

Need to protect student information.

Dependencies between authentication, database and application modules.

MVP should focus on essential features before advanced analytics.

# 4. SCRUM TEAM STRUCTURE

## 4.1 Proposed Team

| Role | Assigned Responsibility |
| --- | --- |
| Product Owner | Defines requirements, represents stakeholders, prioritizes backlog and accepts completed work. |
| Scrum Master | Facilitates Scrum events, removes impediments and supports Agile practices. |
| Development Team | Designs, develops, tests, documents and demonstrates the software. |
| UI/UX Responsibility | Designs simple dashboards and user flows. |
| Testing Responsibility | Verifies acceptance criteria and reports defects. |
| DevOps Responsibility | Supports repository, CI/CD and deployment automation. |

## 4.2 Product Owner Responsibilities

Maintain the product vision.

Prioritize the Product Backlog.

Clarify requirements.

Represent student, faculty and administrator needs.

Review Sprint outcomes and accept completed work.

## 4.3 Scrum Master Responsibilities

Conduct Sprint Planning, Daily Scrum, Review and Retrospective.

Help remove blockers.

Encourage collaboration.

Promote transparency and continuous improvement.

## 4.4 Development Team Responsibilities

Convert User Stories into working software.

Write and review code.

Perform testing.

Maintain technical documentation.

Demonstrate completed features.

# 5. PROJECT EPICS

The complete product is divided into high-level functional modules called Epics. Each Epic contains related features and User Stories.

| Epic | Purpose | Major Features |
| --- | --- | --- |
| Epic 1 – Student Management | Manage student records. | Registration, profile, search, update, delete |
| Epic 2 – Course Management | Manage courses and registrations. | Add course, update course, assign students, view details |
| Epic 3 – Attendance Management | Record and monitor attendance. | Record attendance, view attendance, reports |
| Epic 4 – Marks & Academic Performance | Manage academic marks and results. | Enter marks, update marks, grades, result sheets |
| Epic 5 – Authentication & Security | Protect system access. | Login, logout, password reset, role-based access |
| Epic 6 – Notifications | Provide important academic alerts. | Attendance, examination and result notifications |
| Epic 7 – Reporting | Generate useful academic reports. | Student, attendance, performance and course reports |

# 6. USER STORIES

User Stories describe features from the perspective of the user. The format used is: “As a [user], I want [capability] so that [benefit].”

| ID | Role | I want to… | So that… |
| --- | --- | --- | --- |
| US-01 | Student | log in securely | I can access my academic dashboard safely. |
| US-02 | Administrator | register a new student | the institution can maintain a complete student record. |
| US-03 | Student | view my profile | I can check my personal and academic information. |
| US-04 | Administrator | search for a student | I can retrieve records quickly. |
| US-05 | Administrator | add a course | available courses can be maintained. |
| US-06 | Student | view my registered courses | I know which subjects I am enrolled in. |
| US-07 | Faculty Member | record attendance | attendance records remain accurate and updated. |
| US-08 | Student | view my attendance percentage | I can monitor my attendance. |
| US-09 | Examination Staff | enter examination marks | student performance can be recorded. |
| US-10 | Student | view my results | I can quickly check examination performance. |
| US-11 | Administrator | generate attendance reports | academic information can be reviewed efficiently. |
| US-12 | Student | receive important notifications | I do not miss important academic information. |
| US-13 | Administrator | manage user roles | only authorized users can access restricted functions. |
| US-14 | Faculty Member | search students in my course | I can manage academic work efficiently. |
| US-15 | Administrator | generate student academic reports | reports can be prepared without manual compilation. |

# 7. ACCEPTANCE CRITERIA

Acceptance Criteria define measurable conditions that must be satisfied before a User Story is considered complete.

## US-01 Student Login

Login page loads successfully.

Registered users can enter valid credentials.

Invalid credentials show an error.

Successful login opens the correct dashboard.

Unauthorized users cannot access protected pages.

## US-02 Register Student

Authorized administrator can open registration form.

Required student details can be entered.

Valid data is saved successfully.

Duplicate student IDs are prevented.

New student appears in search results.

## US-05 Add Course

Authorized user can add a course.

Course code is required.

Duplicate course codes are prevented.

Saved course is visible in course list.

## US-07 Record Attendance

Faculty can select a course.

Faculty can select a lecture date.

Student list is displayed.

Attendance can be marked.

Attendance is saved and can be viewed later.

## US-10 View Results

Student can open result section.

Available results are displayed correctly.

Marks and grades are shown clearly.

Student cannot view another student's result.

## US-11 Attendance Report

Authorized user can select course/student.

Attendance data is retrieved correctly.

Report can be displayed.

Report contains required attendance information.

# 8. PRODUCT BACKLOG

The Product Backlog contains the User Stories required to develop the product. Priorities are based on business value, user importance, technical dependency and implementation complexity.

| ID | Epic | User Story | Priority | Story Points |
| --- | --- | --- | --- | --- |
| PBI-01 | Authentication | US-01 Student Login | High | 5 |
| PBI-02 | Student Management | US-02 Register Student | High | 5 |
| PBI-03 | Student Management | US-03 View Profile | High | 3 |
| PBI-04 | Student Management | US-04 Search Student | High | 3 |
| PBI-05 | Course Management | US-05 Add Course | High | 3 |
| PBI-06 | Course Management | US-06 View Registered Courses | High | 3 |
| PBI-07 | Attendance | US-07 Record Attendance | High | 5 |
| PBI-08 | Attendance | US-08 View Attendance | High | 3 |
| PBI-09 | Marks & Performance | US-09 Enter Marks | High | 5 |
| PBI-10 | Marks & Performance | US-10 View Results | High | 3 |
| PBI-11 | Reporting | US-11 Attendance Report | Medium | 5 |
| PBI-12 | Notifications | US-12 Academic Notifications | Medium | 5 |
| PBI-13 | Security | US-13 Manage User Roles | High | 5 |
| PBI-14 | Student Management | US-14 Course-wise Student Search | Medium | 3 |
| PBI-15 | Reporting | US-15 Academic Report | Medium | 5 |

# 9. STORY POINT ESTIMATION

Story Points represent relative effort and complexity rather than exact hours. The project uses a Fibonacci-style scale.

| Story Points | Complexity | Meaning |
| --- | --- | --- |
| 1 | Very Easy | Small change with minimal work. |
| 2 | Easy | Simple feature with limited dependencies. |
| 3 | Moderate | Normal development and testing effort. |
| 5 | Difficult | Multiple steps or dependencies. |
| 8 | Very Difficult | Large feature that may need to be split. |
| 13 | Highly Complex | Very large or uncertain work; should normally be divided. |

## 9.1 Estimation Approach

The team can use Planning Poker. Each member independently selects a point value, explains the reasoning when estimates differ, and agrees on a final estimate. This reduces the influence of one person's estimate and encourages team discussion.

## 9.2 Estimation Summary

The selected backlog contains a mixture of 3- and 5-point stories. Higher-point stories such as attendance recording, mark entry, notifications and reporting involve more validation, data handling or dependencies.

# 10. SPRINT PLANNING

## 10.1 Sprint Duration

A two-week Sprint is proposed for the mini project. The team plans a Sprint Goal, selects prioritized Product Backlog Items, defines tasks and agrees on the expected Sprint deliverable.

## 10.2 Sprint 1 – Foundation and Authentication

| Item | Planned Work |
| --- | --- |
| Goal | Create project foundation and secure user access. |
| Stories | US-01, US-13 |
| Tasks | Repository setup, database foundation, login UI, authentication, role checks, basic testing. |
| Expected Deliverable | Working login and role-based access foundation. |
| Definition of Done | Code reviewed, tests completed, acceptance criteria met and demo-ready. |

## 10.3 Sprint 2 – Student and Course Management

| Item | Planned Work |
| --- | --- |
| Goal | Provide core student and course management. |
| Stories | US-02, US-03, US-04, US-05, US-06 |
| Tasks | Student forms, profile view, search, course form, course list, validation and testing. |
| Expected Deliverable | Working student and course modules. |

## 10.4 Sprint 3 – Attendance and Results

| Item | Planned Work |
| --- | --- |
| Goal | Implement attendance and academic performance. |
| Stories | US-07, US-08, US-09, US-10 |
| Tasks | Attendance interface, attendance storage, marks entry, grade/result view and testing. |
| Expected Deliverable | Working attendance and result modules. |

## 10.5 Sprint 4 – Reports and Notifications

| Item | Planned Work |
| --- | --- |
| Goal | Complete useful reporting and notifications. |
| Stories | US-11, US-12, US-14, US-15 |
| Tasks | Report filters, report generation, notification logic, search improvements and final testing. |
| Expected Deliverable | MVP-ready reporting and notification capabilities. |

# 11. SPRINT BACKLOG

| Sprint | Task | Description | Points |
| --- | --- | --- | --- |
| Sprint 1 | Repository setup | Project repository and basic structure | 2 |
| Sprint 1 | Student/User login | Login page and authentication | 5 |
| Sprint 1 | Role management | Role checks for users | 5 |
| Sprint 2 | Student registration | Student registration form and storage | 5 |
| Sprint 2 | Student search/profile | Search and profile view | 6 |
| Sprint 2 | Course management | Add and view courses | 3 |
| Sprint 2 | Course registration | Display registered courses | 3 |
| Sprint 3 | Attendance recording | Record and save attendance | 5 |
| Sprint 3 | Attendance view | Student attendance percentage | 3 |
| Sprint 3 | Marks entry | Enter and update marks | 5 |
| Sprint 3 | Result view | Display marks and grades | 3 |
| Sprint 4 | Attendance report | Generate filtered report | 5 |
| Sprint 4 | Academic report | Generate student report | 5 |
| Sprint 4 | Notifications | Attendance/examination/result alerts | 5 |

# 12. SCRUM BOARD

The Scrum Board provides a visual view of work status. Items move from Backlog to To Do, In Progress, Testing and Completed.

| Backlog | To Do | In Progress | Testing | Completed |
| --- | --- | --- | --- | --- |
| Academic analytics | Academic report | Attendance module | Login tests | Repository setup |
| Advanced notifications | Result module | Student search | Course tests | Basic UI |
| Future integrations | Course registration | Marks entry | Student tests | Project structure |

## 12.1 Board Usage Rules

Only prioritized work enters the Sprint.

A task in progress should have a clear owner.

Testing begins after development is complete.

Completed means the agreed Definition of Done is satisfied.

Blocked tasks should be discussed in the Daily Scrum.

# 13. DEFINITION OF DONE

A Product Backlog Item is considered Done when:

The User Story is implemented.

All Acceptance Criteria are satisfied.

Relevant functional testing is completed.

No critical defect remains.

Code is reviewed and stored in version control.

Documentation is updated where required.

The feature is demonstrated during the Sprint Review.

The Product Owner accepts the completed work.

# 14. SCRUM CEREMONIES

## 14.1 Sprint Planning

The team reviews the Product Backlog, selects high-priority stories, estimates work, identifies dependencies and defines the Sprint Goal.

## 14.2 Daily Scrum

The team conducts a short daily meeting. Each member discusses what was completed, what will be done next and any challenge or blocker affecting progress.

## 14.3 Sprint Review

At the end of the Sprint, the team demonstrates completed functionality to stakeholders. Feedback is collected and may result in changes to the Product Backlog.

## 14.4 Sprint Retrospective

The team discusses what went well, what problems occurred and what should be improved in the next Sprint.

| Ceremony | Purpose | Output |
| --- | --- | --- |
| Sprint Planning | Plan the Sprint | Sprint Goal and Sprint Backlog |
| Daily Scrum | Synchronize work | Updated plan and blockers |
| Sprint Review | Inspect product increment | Stakeholder feedback |
| Sprint Retrospective | Improve team process | Action items for next Sprint |

# 15. SAMPLE DAILY SCRUM LOG

| Team Member | Yesterday | Today | Blocker |
| --- | --- | --- | --- |
| Member 1 | Completed login UI | Connect login to backend | None |
| Member 2 | Created student schema | Implement student registration | Database validation |
| Member 3 | Prepared test cases | Test authentication | Waiting for build |
| Member 4 | Designed dashboard | Implement profile screen | None |

# 16. SPRINT REVIEW REPORT

## 16.1 Sprint Review – Sample

The team demonstrates the completed Sprint increment to stakeholders. For Sprint 1, the demonstration includes repository setup, login interface, successful authentication and basic role-based access.

## 16.2 Feedback

Login should display clear validation messages.

Student dashboard should show attendance prominently.

Unauthorized users should receive a clear access message.

The interface should use simple labels and navigation.

## 16.3 Action from Feedback

The feedback is converted into Product Backlog improvements. Attendance visibility is given higher priority because it directly affects student usability.

# 17. SPRINT RETROSPECTIVE REPORT

| Area | Observation | Improvement |
| --- | --- | --- |
| What went well | Backlog was clearly prioritized. | Continue using clear priorities. |
| What went well | Team communicated blockers. | Maintain daily Scrum discipline. |
| Challenge | Authentication depended on database setup. | Complete technical dependencies earlier. |
| Challenge | Some estimates differed significantly. | Use Planning Poker and discuss assumptions. |
| Improvement | Testing started late. | Prepare test cases before implementation finishes. |

# 18. RELEASE ROADMAP

| Release | Main Content | Expected Outcome |
| --- | --- | --- |
| Release 0.1 | Project setup and authentication | Users can access the system securely. |
| Release 0.2 | Student and course management | Core academic records can be maintained. |
| Release 0.3 | Attendance and results | Academic performance workflows become usable. |
| Release 1.0 | Reports, notifications and MVP stabilization | Essential academic management MVP is ready. |

## 18.1 Future Enhancements

Advanced academic analytics.

AI-based academic recommendations.

Mobile application.

External institutional integrations.

Advanced dashboards.

Automated infrastructure and monitoring improvements.

# 19. AGILE FRAMEWORK COMPARISON

| Framework | Main Idea | Advantages | Suitability |
| --- | --- | --- | --- |
| Scrum | Iterative work in fixed Sprints with defined roles and ceremonies. | Clear structure, frequent review and incremental delivery. | High |
| Kanban | Continuous flow using visual work limits. | Flexible and simple workflow management. | Medium |
| Extreme Programming (XP) | Strong engineering practices and frequent feedback. | Useful for code quality and testing. | Medium |
| Lean Development | Reduce waste and maximize value. | Focuses on efficiency and value. | Medium |
| LeSS | Scale Scrum across multiple teams. | Useful when one product grows across teams. | Low initially |
| SAFe | Structured scaling of Agile across an enterprise. | Supports large organizations and coordination. | Low for a small student team |
| Scrum@Scale | Coordinates multiple Scrum teams. | Useful for scaling Scrum. | Low initially |

## 19.1 Recommended Framework

Scrum is the most suitable framework for the initial project because the platform can be developed incrementally, the team can work in short Sprints, and the backlog can be reviewed and reprioritized after each Sprint. As the product grows to multiple development teams, a scaling framework could be considered.

# 20. RISK MANAGEMENT

| Risk | Impact | Probability | Mitigation |
| --- | --- | --- | --- |
| Incorrect requirements | High | Medium | Review User Stories and Acceptance Criteria with stakeholders. |
| Data errors | High | Medium | Use validation, testing and controlled updates. |
| Security problems | High | Medium | Use authentication, authorization and secure communication. |
| Sprint overloading | Medium | Medium | Select realistic backlog items based on capacity. |
| Technical dependency delays | Medium | Medium | Identify dependencies during Sprint Planning. |
| Late testing | Medium | Medium | Prepare test cases early and test continuously. |
| Scope expansion | Medium | High | Keep advanced features outside the MVP unless reprioritized. |

# 21. COMMUNICATION AND COLLABORATION PLAN

| Activity | Frequency | Participants | Purpose |
| --- | --- | --- | --- |
| Daily Scrum | Daily | Development Team | Track progress and blockers. |
| Sprint Planning | Start of Sprint | Entire Scrum Team | Select work and define Sprint Goal. |
| Sprint Review | End of Sprint | Team + Stakeholders | Demonstrate increment and collect feedback. |
| Sprint Retrospective | End of Sprint | Scrum Team | Improve process. |
| Backlog Refinement | As needed | PO + Team | Clarify and prepare future stories. |

# 22. AGILE METRICS

The team can use simple Agile metrics to understand progress without using them as a measure of individual performance.

Sprint Velocity: Story Points completed in a Sprint.

Burndown: Remaining work across the Sprint.

Cycle Time: Time taken for a work item to move from start to completion.

Defect Count: Number of defects found during testing.

Story Completion Rate: Percentage of planned stories completed.

## 22.1 Sample Burndown Data

| Sprint Day | Remaining Story Points |
| --- | --- |
| 1 | 23 |
| 2 | 21 |
| 3 | 19 |
| 4 | 17 |
| 5 | 15 |
| 6 | 12 |
| 7 | 9 |
| 8 | 6 |
| 9 | 3 |
| 10 | 0 |

# 23. PRODUCT BACKLOG PRIORITIZATION RATIONALE

High-priority items are those required for the core product to work or those that provide direct value to the primary users. Authentication is prioritized because protected academic data should not be accessible without authorization. Student management, course registration, attendance and results form the main academic workflow. Reporting and notifications follow after the core records and workflows are available.

| Priority | Reason | Examples |
| --- | --- | --- |
| High | Essential for MVP and core user workflow. | Login, student registration, attendance, marks, results. |
| Medium | Useful after core workflows are stable. | Reports, notifications, advanced search. |
| Low | Non-essential or future enhancement. | Advanced analytics, external integrations. |

# 24. TRACEABILITY: VISION TO SPRINT

| Product Objective | Epic | User Stories | Sprint |
| --- | --- | --- | --- |
| Secure access | Authentication & Security | US-01, US-13 | Sprint 1 |
| Centralized student records | Student Management | US-02, US-03, US-04 | Sprint 2 |
| Course management | Course Management | US-05, US-06 | Sprint 2 |
| Efficient attendance | Attendance Management | US-07, US-08, US-11 | Sprint 3–4 |
| Academic performance | Marks & Performance | US-09, US-10 | Sprint 3 |
| Academic communication | Notifications | US-12 | Sprint 4 |
| Efficient reporting | Reporting | US-11, US-15 | Sprint 4 |

# 25. EXPECTED MVP

The MVP is the first usable version of the platform. It focuses on essential academic management functions rather than advanced features.

Secure login and role-based access.

Student registration and profile management.

Course registration and course information.

Attendance recording and viewing.

Examination and result management.

Basic academic and attendance reports.

## 25.1 MVP Exclusions

AI-based recommendations.

Advanced analytics.

Complex external integrations.

Large-scale multi-institution support.

Non-essential automation.

# 26. PROJECT TIMELINE

| Week | Planned Activity | Deliverable |
| --- | --- | --- |
| Week 1 | Product review and backlog preparation | Agile product plan |
| Week 2 | Sprint 1 – Authentication | Working login and roles |
| Week 3–4 | Sprint 2 – Student/Course | Student and course modules |
| Week 5–6 | Sprint 3 – Attendance/Results | Attendance and result modules |
| Week 7–8 | Sprint 4 – Reports/Notifications | MVP completion |
| Week 9 | Final testing and review | Stable project increment |
| Week 10 | Documentation and final presentation | Agile project report |

# 27. CONCLUSION

This Unit 2 Agile Mini Project converts the Enterprise Student Record and Academic Management Platform from a product discovery concept into a structured Agile development plan. The product is divided into Epics and User Stories, and each story has measurable Acceptance Criteria. A prioritized Product Backlog and Story Point estimates provide a clear basis for incremental development.

The proposed four-Sprint plan starts with authentication and project foundations, continues with student and course management, then develops attendance and results, and finally completes reporting and notifications. Scrum ceremonies provide regular opportunities to inspect progress, demonstrate working features and improve the development process.

Scrum is recommended for the initial project because it provides a practical structure for a small team and supports incremental delivery. The resulting plan provides a clear connection between business objectives, user needs, backlog items, Sprint work and the final MVP.

# 28. FINAL DELIVERABLE CHECKLIST

| Deliverable | Status / Evidence |
| --- | --- |
| Agile Project Planning Report | Included |
| Product Vision Document | Included in Sections 2–3 |
| Scrum Team Structure | Included in Section 4 |
| Scrum Roles and Responsibilities | Included in Section 4 |
| Epic Documentation | Included in Section 5 |
| User Story Repository | Included in Section 6 |
| Acceptance Criteria Document | Included in Section 7 |
| Prioritized Product Backlog | Included in Section 8 |
| Story Point Estimation Sheet | Included in Section 9 |
| Sprint Planning Document | Included in Section 10 |
| Sprint Backlog | Included in Section 11 |
| Scrum Board | Included in Section 12 |
| Definition of Done | Included in Section 13 |
| Scrum Ceremonies | Included in Section 14 |
| Sprint Review Report | Included in Section 16 |
| Sprint Retrospective Report | Included in Section 17 |
| Agile Framework Comparison | Included in Section 19 |
| Risk Management | Included in Section 20 |
| Project Timeline and Release Roadmap | Included in Sections 18 and 26 |